## Sheet1
# | Reported Date | Reported by | Severity [P0-P5] | Status [open, in-progress, resolved, won't fix] | Assigned To | Short Desc. | Expected Results | Actual Results | Steps to reproduce | Issue Link | Severity Description P0 crash bug; game crashes and is unrecoverable P1 game stopping bug, but no crash; cannot keep playing P2 serious, game not working as expected P3 annoying, could ship but loss of marks P4 annoying or limiting, but could be shipped as-is P5 minor or feature that nice to have but could ship in future release
| 2024-02-15 | Andrew | P5 | resolved | Andrew | bullets spawn on top of spaceship | bullets should be rendered below | bullets spawn on top of spaceship | fire some bullets
| 2024-02-16 | Andrew | P3 | resolved | Celvin | collision model inconsistency. | direction of collision shouldn't matter for effectiveness of detection | when firing down-left collision model "misses" more than top-right | shoot bullets at corners. removed as soon as they hit top-right corner, not removed as soon as they hit bottom-left corner
| 2024-02-16 | Alex | P3 | resolved | Celvin | can go inside the walls, obstacles and enemies (only when facing left and bottom). must be the collision | character should bounce back | can go into the walls and freely move around | while facing down or left, you can pass through and go into the walls, obstacles and enemies.
| 2024-03-04 | Alex | P3 | resolved | Shafquat | bullet collision. bullets can go through obstacles, and hit the enemies | bullets should disapear after hitting a wall or an obstacle | bullets go through them | shoot a bullet through an obstacle and it'll go through and hit an enemy
| 2024-03-05 | Nate | P4 | resolved | Andrew | sprites appear transparent | sprites should be opaque | sprites appear transparent | simply playing the game
| 2024-03-05 | Nate | P3 | resolved | Celvin | when entering a new room, player cannot collide with the bottom right or top left corners | player should collide with the corners | player phases through | enter a new room -> collide with corners
| 2024-03-09 | Nate | P4 | resolved | Nate | Shotgun audio messes with the initial reload sound and the explosion sound | player should be able to hear the initial reload sound and explosions sound | player does not hear any audio following a shotgun sound | shoot the shotgun and listen to the audio | https://github.students.cs.ubc.ca/CPSC427-2023W-T2/Team10-Touch-Of-The-Void/issues/54
| 2024-03-24 | Alex | P3 | resolved | Celvin | top left and bottom right corner wall bug player can go into it, and be stuck | bounce off the walls that are at and near the corners | player gets prisoned in the very corner wall, unable to escape unless you restart the game | fly into the top left or bottom right walls
| 2024-03-24 | Alex | P4 | resolved |  | Enemies can go through obstacles and shoot through obstacles. Enemies dont move sometimes | shouldn't be able to shoot or move through obstacles | enemies can shoot and move through them. | it happens after clearing a few rooms but only sometimes. it occurs in the "boss room" sometimes, maybe it's related to it
| 2024-04-09 | Andrew | P4 | open |  | Enemies can see through diagonal corners i.e. where 0 is empty and 1 is obstacle [0,1] [1,0] | Shouldn't be able to see through surfaces | Is able to see you through a wall | Get an Ai to look at you through a corner
| 2024-04-09 | Andrew | P2 | resolved | Andrew | Enemy (& Boss) rockets do not explode | When enemy rocket launchers shoot their rockets should explode | They just colide and disappear | Spawn an enemy rocket projectile
| 2024-04-09 | Andrew | P2 | resolved | Shafquat | Enemy flamethrowers do not cause the player to go on fire | When the player is hit with a flame attack, they should be be set on fire | The flame projectiles collide and disappear | Spawn an enemy flamethrower, and get them to fire and hit you
| 2024-04-09 | Andrew | P4 | resolved | Andrew | Boss shielding animation, replays instead of plays one then stops, and then plays in reverse | When the Boss is shielding, they should stay shielded until the shield is done | The boss is continuosly raising their shield, then resetting and repeating | Get to the shielding face of the boss fight
| 2024-04-09 | Andrew | P3 | resolved | Nate | Enemy projectiles (specifically in the boss phase, have way too large hitboxes) | When the player is not visually near an enemy projectile, it should not hit them. | The projectiles are triggering collission, before they actually reach or even hit the player | Try getting real close but not touching a rocket projectile in the boss fight |  | We probably just need to generate the mesh's using celvin's script
| 2024-04-09 | Andrew | P3 | resolved | Andrew | Another enemy can push, the turret off of it's stand | The turret is locked in place | A turret can be pushed off of it's stand by say a melee enemy | Try standing in between a melee enemy and a turret